## 📅 Roadmap Tracker
🏙️ NEIGHBOURHOOD LIVABILITY INDEX — Project Tracker
Analytics Engineering Project ¦ 12-Week Delivery Plan ¦ demografy.com.au
# | Task Name | Description | Deliverable | Week | Status | Priority | Notes
PHASE 0 — Brainstorm & Setup
0.1 | Finalise 5 livability metrics | Confirm: cafes, parks, gyms, childcare, transport | Metrics doc / Notion page | 1 | Not Started | 🔴 High | Match to Google Places types
0.2 | Create GitHub repo | Initialise repo, add .gitignore, README skeleton | Public GitHub repo | 1 | Not Started | 🔴 High | Branching strategy: main + dev
0.3 | Set up Supabase project | Create project, save connection string in .env | Live Supabase project | 1 | ✅ Done | 🔴 High | Already have account ✓
0.4 | Activate Google Places API | Enable Places API (New), get API key, set billing alert | API key in .env | 1 | ✅ Done | 🔴 High | Already have key ✓
0.5 | Design DB schema (ERD) | Plan raw_places + suburb_metrics table structures | ERD diagram / SQL DDL | 2 | Not Started | 🟡 Med | See Schema sheet
PHASE 1 — Architecture & Connectivity
1.1 | Scaffold Streamlit app | Create app.py with two suburb text inputs + basic layout | Running local Streamlit app | 2 | Not Started | 🔴 High | pip install streamlit
1.2 | Connect app to Supabase | Use supabase-py client; test read/write with dummy row | Confirmed DB connection | 2 | Not Started | 🔴 High | Store creds in st.secrets
1.3 | Write check_suburb_in_db() | SELECT query: does suburb exist in DB? | Function returns True/False | 2 | Not Started | 🔴 High | Core of cache logic
1.4 | Create Supabase tables | Run DDL: raw_places, suburb_metrics (see Schema sheet) | Tables live in Supabase | 2 | Not Started | 🔴 High | Add indexes on suburb_name
1.5 | End-to-end connection test | App reads from DB and prints result in UI | Working demo | 2 | Not Started | 🟡 Med
PHASE 2 — Smart Ingestion Engine
2.1 | Write get_google_data() | Call Places API text search for each category + suburb | Function returns JSON list | 3 | Not Started | 🔴 High | Use Field Masking to cut cost
2.2 | Implement cache-miss logic | If not in DB → call API → save raw JSON to raw_places | Data appears in Supabase | 3 | Not Started | 🔴 High | Heart of the pipeline
2.3 | Implement cache-hit logic | If in DB → skip API, load existing data | No duplicate API calls | 4 | Not Started | 🔴 High | Check updated_at timestamp
2.4 | Add input validation | Handle blank input, unknown suburb, API errors gracefully | Error messages in UI | 4 | Not Started | 🟡 Med | try/except all API calls
2.5 | Test with 3 real suburbs | Run pipeline for Bondi, Fitzroy, Newtown | 3 suburbs in Supabase | 5 | Not Started | 🟡 Med | Verify place counts look right
2.6 | Cost audit | Calculate $ spent per suburb fetch; document in README | Cost estimate doc | 5 | Not Started | ⚪ Low | Target: <$0.01/suburb
PHASE 3 — Real-Time Transformations (dbt)
3.1 | Install & configure dbt Core | pip install dbt-postgres; init dbt project; connect to Supabase | dbt debug passes | 6 | Not Started | 🔴 High | dbt-postgres not dbt-cloud
3.2 | Write stg_places.sql model | Parse raw JSON → one row per place with category tag | Staging table in Supabase | 6 | Not Started | 🔴 High | Use json_array_elements()
3.3 | Write mart_suburb_metrics.sql | Aggregate counts per suburb per category | Gold metrics table | 7 | Not Started | 🔴 High | Final shape for dashboard
3.4 | Trigger dbt from Python | subprocess.run(['dbt', 'run']) after API insert | Auto-transform on cache miss | 7 | Not Started | 🔴 High | Test timing < 5s
3.5 | Write dbt tests | not_null, unique tests on suburb_metrics | dbt test passes | 8 | Not Started | 🟡 Med
3.6 | Document dbt models | Add .yml descriptions for all models | dbt docs generate | 8 | Not Started | ⚪ Low
PHASE 4 — Visualisation & Optimisation
4.1 | Build bar chart comparison | Side-by-side Plotly bar: suburb A vs B per category | Chart renders in app | 9 | Not Started | 🔴 High | Use st.plotly_chart()
4.2 | Build radar / spider chart | Overall livability shape comparison | Radar chart in app | 9 | Not Started | 🟡 Med | Normalise scores 0-10
4.3 | Add map visualisation | Plot amenity locations using Folium or st.map() | Interactive map tab | 9 | Not Started | 🟡 Med | Requires lat/lng from API
4.4 | Add progress bar / spinner | Show step-by-step status during pipeline run | UX loading states | 10 | Not Started | 🟡 Med | st.progress() + st.status()
4.5 | SQL performance tuning | Add indexes, test query time < 1s | Query time benchmarks | 10 | Not Started | 🟡 Med | EXPLAIN ANALYZE in Supabase
4.6 | UI polish & branding | Match demografy.com.au colour palette | Polished dashboard | 10 | Not Started | ⚪ Low
PHASE 5 — Deploy & Embed
5.1 | Deploy to Streamlit Cloud | Push to GitHub → connect to share.streamlit.io | Live public URL | 11 | Not Started | 🔴 High | Free tier sufficient
5.2 | Configure st.secrets in cloud | Add Supabase + Google API keys to Streamlit Cloud secrets | App runs in production | 11 | Not Started | 🔴 High | Never commit .env to git
5.3 | Test IFrame embed | Embed URL in dummy HTML page; test responsiveness | IFrame working | 11 | Not Started | 🔴 High | Add ?embed=true param
5.4 | Write README / documentation | Caching strategy, setup guide, cost analysis | README.md complete | 12 | Not Started | 🟡 Med
5.5 | Final QA & handover | Test 5 suburbs, check all edge cases, demo to stakeholder | Sign-off meeting | 12 | Not Started | 🔴 High

## 🗄️ DB Schema
🗄️ DATABASE SCHEMA — Supabase (PostgreSQL)
TABLE: raw_places
Stores raw API responses. One row per suburb+category fetch.
# | Column Name | Data Type | Constraint | Description
1 | id | UUID | PRIMARY KEY | Auto-generated
2 | suburb_name | TEXT | NOT NULL | e.g. 'Bondi Beach'
3 | category | TEXT | NOT NULL | e.g. 'cafes', 'parks'
4 | api_response | JSONB | NOT NULL | Full Google Places JSON array
5 | place_count | INTEGER |  | Quick count from JSON
6 | fetched_at | TIMESTAMPTZ | DEFAULT now() | When API was called
TABLE: suburb_metrics
Gold table. One row per suburb with all metric counts (output of dbt).
# | Column Name | Data Type | Constraint | Description
1 | id | UUID | PRIMARY KEY | Auto-generated
2 | suburb_name | TEXT | UNIQUE NOT NULL | e.g. 'Bondi Beach'
3 | cafes | INTEGER | DEFAULT 0 | Count of cafes/coffee shops
4 | parks | INTEGER | DEFAULT 0 | Count of parks/gardens
5 | gyms | INTEGER | DEFAULT 0 | Count of gyms/yoga/sports
6 | childcare | INTEGER | DEFAULT 0 | Count of childcare/preschools
7 | transport_stops | INTEGER | DEFAULT 0 | Count of stations/stops
8 | livability_score | NUMERIC(4,2) |  | #NAME?
9 | last_updated | TIMESTAMPTZ | DEFAULT now() | Last dbt run time

## ✅ Phase 1 Checklist
✅ PHASE 1 CHECKLIST — Architecture & Connectivity
# | Step | What to Do | Status | File / Location
1 | Create project folder structure | mkdir neighbourhood-index && cd neighbourhood-index mkdir app db dbt_project tests | Not Started | Terminal
2 | Create virtual environment | python -m venv venv && source venv/bin/activate | Not Started | Terminal
3 | Install dependencies | pip install streamlit supabase python-dotenv plotly pandas | Not Started | requirements.txt
4 | Create .env file | Add SUPABASE_URL, SUPABASE_KEY, GOOGLE_API_KEY (never commit!) | Not Started | .env (gitignored)
5 | Create Supabase tables | Run DDL from Schema sheet in Supabase SQL editor | Not Started | Supabase dashboard
6 | Create db/client.py | Initialise supabase-py client from env vars | Not Started | db/client.py
7 | Create db/queries.py | Write check_suburb_in_db() function | Not Started | db/queries.py
8 | Create app.py skeleton | Two st.text_input() boxes + Connect button | Not Started | app.py
9 | Test DB connection in app | Call check_suburb_in_db('Bondi') and print result in UI | Not Started | app.py
10 | Commit to GitHub | git init, git add ., git commit -m 'Phase 1: connectivity' | Not Started | GitHub